## Sheet1
|  | Week-1 2/08- 2/15 | Week-2 2/16- 2/22 | Week-3 2/23- 3/01 | Week-4 3/02- 3/08 | Week-5 3/09- 3/15 | Week-6 3/16- 3/22 | Week-7 3/23- 3/29 | Week-8 3/30- 4/05 | Week-9 4/06- 4/12 | Week-10 4/13- 4/15 | Completed Tasks
Task ID | Task Name
1 | Problem Understanding | [10 empty] | Completed
1.1 | Prepare document of understanding
2 | Data Identification and Collection
2.1 | Identify sample of twitter users and collect their tweets | [10 empty] | Completed
3 | Implementation
3.1 | Create hash tag library | [10 empty] | Completed
3.2 | Train machine learning model using tweet-emoticon pairs (scikit-learn toolkit) | [10 empty] | Completed
| Write A java program to get users and their respective tweets | [10 empty] | Completed
| Write a Mapreduce job toget User Tweet Pair | [10 empty] | Completed
| Write a Mapreduce job toget User Emotion Pair | [10 empty] | Completed
3.3 | Annotate target user with areas of interest manually | [10 empty] | Completed
3.4 | Calculate Mean Emotion Proportion Score | [10 empty] | Completed
3.5 | Calculate Mean Emotion Distribution Score | [10 empty] | Completed
3.6 | Calculate User Intrest Scores | [10 empty] | Completed
3.7 | Sort interested and disinterested users section | [10 empty] | Completed
4 | Data Analysis and Reporting | [10 empty] | Completed
4.1 | Apply statistical tests to determine if there is a relationship between user Emotions and their area of interest(Mann-Whitney U test) | [10 empty] | Completed
4.2 | Evaluate the quality of prediction model (ROC curve) | [10 empty] | Completed
4.3 | Generate Pearson Correlation Table | [10 empty] | Completed
4.4 | Generate a table presenting the emotional difference value | [10 empty] | Completed
4.5 | Prepare Final Project Report | [10 empty] | Completed